## Cover
TEST REPORT DOCUMENT
Project Name | EnglishLab |  |  | Creator | phongdx
Project Code | SEP490_G23 |  |  | Issue Date | 2026-07-28
Document Code |  |  |  | Version | v4.0
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2026-07-28 | v4.0 | Integration Test design for EnglishLab backend | A | v4 executed 3 rounds on 2026-07-28 against http://localhost:8080; Round statuses filled by live API integration runner | SRS Report3; source tree; srs-usecase-diagram-map.md

## Test Cases
TEST CASE LIST
Project Name
Project Code
Test Environment Setup Description |  | 1. Server: Spring Boot 4 + JDK 21 (@SpringBootTest + MockMvc) 2. Database: PostgreSQL with migrations applied 3. Web Browser: N/A for API Integration Tests (optional Postman/curl) 4. JWT security enabled; roles seeded 5. External PayOS / Mail / Gemini / Lark stubbed or sandbox
No | Function Name | Sheet Name | Description | Pre-Condition
1 | AuthController | IT - Auth | Integrate AuthController with AuthService and persistence for register/verify/login/OTP reset. | DB up; roles seeded; target sheet `IT - Auth` exists; external systems stubbed as needed for this module.
2 | UserController | IT - User | Integrate UserController profile/avatar/password with UserService and UserRepository. | DB up; roles seeded; target sheet `IT - User` exists; external systems stubbed as needed for this module.
3 | StudentNotificationController | IT - Notif | Integrate notification preferences and AppNotification list/read flows. | DB up; roles seeded; target sheet `IT - Notif` exists; external systems stubbed as needed for this module.
4 | StudentCommerceController | IT - Commerce | Integrate StudentCommerceController cart/wishlist with StudentCommerceService persistence. | DB up; roles seeded; target sheet `IT - Commerce` exists; external systems stubbed as needed for this module.
5 | StudentPaymentController | IT - Payment | Integrate payment link/quote, payment_orders persistence and PayOS webhook side effects. | DB up; roles seeded; target sheet `IT - Payment` exists; external systems stubbed as needed for this module.
6 | PublicOnlineCourseController | IT - Course | Integrate public catalog and learner content/progress through OnlineCourseService. | DB up; roles seeded; target sheet `IT - Course` exists; external systems stubbed as needed for this module.
7 | CourseDiscussionController | IT - Discuss | Integrate discussion create/reply/report and CM moderation through discussion services. | DB up; roles seeded; target sheet `IT - Discuss` exists; external systems stubbed as needed for this module.
8 | ContentManagerOnlineCourseController | IT - Content | Integrate Content Manager online course CRUD/publish/version/category flows. | DB up; roles seeded; target sheet `IT - Content` exists; external systems stubbed as needed for this module.
9 | LearningPackageManagementController | IT - Package | Integrate CM package/bundle management through LearningPackageManagementService. | DB up; roles seeded; target sheet `IT - Package` exists; external systems stubbed as needed for this module.
10 | ContentManagerCurriculumController | IT - Curriculum | Integrate curriculum programs/units, exercise bank, rubrics and learning paths. | DB up; roles seeded; target sheet `IT - Curriculum` exists; external systems stubbed as needed for this module.
11 | ManagerEnrollmentController | IT - EnrollReq | Integrate learner enrollment requests and staff processing via EnrollmentRequestService. | DB up; roles seeded; target sheet `IT - EnrollReq` exists; external systems stubbed as needed for this module.
12 | TrainingManagerClassroomController | IT - Classroom | Integrate public offerings and TM enrollment/teacher operations via ClassroomOfferingService. | DB up; roles seeded; target sheet `IT - Classroom` exists; external systems stubbed as needed for this module.
13 | StudentClassroomController | IT - LearnerCls | Integrate assigned learner classroom access, homework submit, materials and tuition proofs. | DB up; roles seeded; target sheet `IT - LearnerCls` exists; external systems stubbed as needed for this module.
14 | TeacherClassroomController | IT - Teacher | Integrate teacher homework, attendance, gradebook and change-request flows. | DB up; roles seeded; target sheet `IT - Teacher` exists; external systems stubbed as needed for this module.
15 | ClassroomQuizController | IT - Quiz | Integrate teacher quiz lifecycle and learner submit through ClassroomQuizService. | DB up; roles seeded; target sheet `IT - Quiz` exists; external systems stubbed as needed for this module.
16 | PlacementTestController | IT - Assess | Integrate placement, course assessment and mock-test submit flows; AI clients mocked. | DB up; roles seeded; target sheet `IT - Assess` exists; external systems stubbed as needed for this module.
17 | StudentSupportTicketController | IT - Support | Integrate learner ticket create/reply and staff claim/update via SupportTicketService. | DB up; roles seeded; target sheet `IT - Support` exists; external systems stubbed as needed for this module.
18 | AdminUserController | IT - Admin | Integrate admin user/role/status/audit flows through AdminUserService. | DB up; roles seeded; target sheet `IT - Admin` exists; external systems stubbed as needed for this module.
19 | LarkWebhookController | IT - Lark | Integrate Lark webhook handling and staff sync-lark through Lark services. | DB up; roles seeded; target sheet `IT - Lark` exists; external systems stubbed as needed for this module.
20 | TrainingManagerInfrastructureController | IT - Infra | Integrate campuses/rooms/templates and generate-sessions via ClassroomInfrastructureService. | DB up; roles seeded; target sheet `IT - Infra` exists; external systems stubbed as needed for this module.
21 | TrainingManagerDashboardController | IT - Report | Integrate TM/staff dashboard and CM revenue analytics endpoints. | DB up; roles seeded; target sheet `IT - Report` exists; external systems stubbed as needed for this module.
22 | ManagerClassroomController | IT - Proposal | Integrate staff proposal submit and manager approve/reject via ClassroomProposalService. | DB up; roles seeded; target sheet `IT - Proposal` exists; external systems stubbed as needed for this module.
23 | ClassroomAttendanceDisputeController | IT - Dispute | Integrate learner dispute create and teacher review via ClassroomAttendanceDisputeService. | DB up; roles seeded; target sheet `IT - Dispute` exists; external systems stubbed as needed for this module.
24 | StudentClassroomController | IT - Notes | Integrate learner lesson notes CRUD through LearnerLearningExperienceService. | DB up; roles seeded; target sheet `IT - Notes` exists; external systems stubbed as needed for this module.

## Test Statistics
TEST STATISTICS
Project Name |  |  | Creator | phongdx
Project Code |  |  | Reviewer/Approver
Document Code |  |  | Issue Date |  |  | 2026-07-28
Notes | Release Integration Test pack includes 24 modules: AUTH, USER, NOTIF, COMMERCE, PAYMENT, COURSE, DISCUSS, CONTENT, PACKAGE, CURRICULUM, ENROLLREQ, CLASS, LEARNERCLS, TEACH, QUIZ, ASSESS, SUPPORT, ADMIN, LARK, INFRA, REPORT, PROPOSAL, DISPUTE, NOTES
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
Sub total
| Test coverage |  |  | %
| Test successful coverage |  |  | %

## IT - Auth
Feature | AuthController | [13 empty] | Passed
Test requirement | Integrate AuthController with AuthService and persistence for register/verify/login/OTP reset. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Register & verify
IT_AUTH_01 | Verify registering an account through AuthController persists user and verification token via AuthService. | 1. Call POST /api/auth/register via MockMvc with a unique email, password and fullName. 2. AuthController.register() delegates to AuthService.register(). 3. AuthService creates the account through UserRepository.save() and stores a verification OTP through AuthTokenRepository. 4. Query the users and auth_tokens tables for the new email. | Response is 200/201 with a success message. One users row is inserted with hashed password (not plaintext). One verification auth_tokens row is linked to that user. No access token is required for this call. | Database is available; email is unused; mail sender is stubbed. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | register HTTP 200
IT_AUTH_02 | Verify duplicate registration is rejected by AuthService without inserting a second users row. | 1. Seed an existing LEARNER in users. 2. Call POST /api/auth/register via MockMvc with the same email. 3. AuthController delegates to AuthService.register() which checks UserRepository before insert. 4. Count users rows for that email. | Response is 4xx with a duplicate-email business error. Exactly one users row remains for the email. No extra verification token is created for a second account. | An active user with the target email already exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | duplicate register (negative) HTTP 400
IT_AUTH_03 | Verify email verification activates the account through AuthService and AuthTokenRepository. | 1. Register a user and read the OTP from auth_tokens. 2. Call POST /api/auth/verify-email via MockMvc with email and OTP. 3. AuthController.verifyEmail() delegates to AuthService.verifyEmail(). 4. AuthService validates the token via AuthTokenRepository and updates the user via UserRepository. 5. Reload users and auth_tokens. | Response is 200 OK. users.email_verified becomes true. Verification token is consumed/expired per AuthService rules. Subsequent login with the password succeeds. | A pending verification user and valid OTP exist. | Failed | 2026-07-28 | phongdx | Failed | 2026-07-28 | phongdx | Failed | 2026-07-28 | phongdx | verify-email happy-path expected [200, 201] got 400: {"status":400,"message":"M? x?c th?c l? b?t bu?c"}
IT_AUTH_04 | Verify invalid OTP is rejected and leaves the user unverified. | 1. Seed an unverified user with a real OTP in auth_tokens. 2. Call POST /api/auth/verify-email via MockMvc with a wrong OTP. 3. AuthService.verifyEmail() validates against AuthTokenRepository and must not update UserRepository verification flag. 4. Query users.email_verified. | Response is 4xx. email_verified remains false. Account is not activated. | An unverified user exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | invalid OTP (negative) HTTP 400
Login & security
IT_AUTH_05 | Verify login through AuthController returns a JWT accepted by the security filter and UserController. | 1. Seed a verified LEARNER with a known password hash. 2. Call POST /api/auth/login via MockMvc. 3. AuthController.login() delegates to AuthService.login() which authenticates via UserRepository/UserDetails. 4. Call GET /api/user/me via MockMvc with Authorization Bearer accessToken. 5. JwtAuthenticationFilter authenticates the request before UserController.getCurrentUser(). | Login response is 200 OK and contains accessToken plus user payload. GET /api/user/me returns 200 with the same email/id. JWT subject matches the authenticated user. | A verified LEARNER account exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | login + me HTTP 200
IT_AUTH_06 | Verify wrong password login fails in AuthService and issues no usable token. | 1. Seed a verified user. 2. Call POST /api/auth/login via MockMvc with an incorrect password. 3. AuthService.login() rejects authentication before issuing JWT. | Response is 401/403. No valid accessToken is returned. Protected endpoints remain inaccessible without a token. | A verified user exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | bad password (negative) HTTP 401
IT_AUTH_07 | Verify missing JWT is blocked by SecurityFilterChain before UserController executes. | 1. Call GET /api/user/me via MockMvc without Authorization header. 2. Observe that JwtAuthenticationFilter / authorizeHttpRequests rejects the call before UserService is invoked. | Response is 401 or 403. No UserResponse body is returned. Confirms controller-security integration. | Spring Security configuration is active. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | me without token (negative) HTTP 403
Password recovery
IT_AUTH_08 | Verify forgot-password and reset-password flow updates credentials through AuthService. | 1. Seed a verified user and capture the current password hash. 2. Call POST /api/auth/forgot-password via MockMvc. 3. AuthService creates a reset token via AuthTokenRepository. 4. Call POST /api/auth/reset-password via MockMvc with OTP and new password. 5. AuthService updates the hash via UserRepository.save(). 6. Login with the new password and attempt the old password. | Forgot-password returns a generic success response. Reset succeeds and users.password hash changes. Login works only with the new password. | Verified user exists; mail is stubbed. | Passed | 2026-07-28 | phongdx | Failed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | forgot-password happy-path HTTP 200
IT_AUTH_09 | Verify invalid reset OTP does not change the password hash. | 1. Seed a verified user and capture password hash. 2. Call POST /api/auth/reset-password via MockMvc with an invalid OTP. 3. AuthService.resetPassword() rejects via AuthTokenRepository validation. 4. Compare password hash in users. | Response is 4xx. Password hash is unchanged. Old credentials still authenticate. | A verified user exists. | Failed | 2026-07-28 | phongdx | Failed | 2026-07-28 | phongdx | Failed | 2026-07-28 | phongdx | forgot before reset 400: {"status":400,"message":"Vui l?ng ch? 54 gi?y tr??c khi g?i l?i OTP."}
IT_AUTH_10 | Verify resend-verification rotates or recreates a verification token through AuthService. | 1. Seed an unverified user. 2. Call POST /api/auth/resend-verification via MockMvc. 3. AuthController delegates to AuthService which writes AuthTokenRepository. 4. Query auth_tokens for an active verification token. | Response is 200 OK. An active verification token exists for the user. No account is marked verified by this call alone. | An unverified user exists; mail is stubbed. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | reset invalid OTP (negative) HTTP 400
Note on E10: ====== ID#AAAB9K9xuaA tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - User
Feature | UserController | [13 empty] | Passed
Test requirement | Integrate UserController profile/avatar/password with UserService and UserRepository. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Profile
IT_USER_01 | Verify fetching the current profile via UserController loads data through UserService and UserRepository. | 1. Authenticate as LEARNER and obtain a JWT. 2. Call GET /api/user/me via MockMvc with the Bearer token. 3. UserController.getCurrentUser() delegates to UserService.getCurrentUser(). 4. UserService loads the account through UserRepository. 5. Compare response fields with the users table row. | Response is 200 OK. Returned JSON contains correct id, email, fullName and role. Values match the users row for the token subject. No other user's data is returned. | A LEARNER account exists and a valid JWT is available. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | GET me HTTP 200
IT_USER_02 | Verify updating profile through UserController persists fields via UserService/UserRepository. | 1. Call PUT /api/user/me via MockMvc with updated fullName/phone/target fields. 2. UserController.updateCurrentUser() delegates to UserService.updateProfile(). 3. UserService saves changes through UserRepository.save(). 4. Query users and call GET /api/user/me again. | Response is 200 OK. Persisted columns match the request payload. GET /api/user/me reflects the updates. | Valid JWT; request passes validation. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | PUT me HTTP 200
IT_USER_03 | Verify change-password requires the current password and updates the hash via UserService. | 1. Call PUT /api/user/me/password via MockMvc with a wrong currentPassword. 2. UserService.changePassword() must reject before UserRepository update. 3. Call PUT again with the correct currentPassword and a newPassword. 4. UserService updates the hash through UserRepository. 5. Login with the new password. | Wrong current password returns 4xx and hash is unchanged. Correct change returns success/204 and hash changes. Login succeeds only with the new password. | Account with a known password exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | wrong current password (negative) HTTP 400
IT_USER_04 | Verify avatar upload through UserController stores a file and updates users.avatar_url. | 1. Call POST /api/user/me/avatar via MockMvc as multipart. 2. UserController.updateAvatar() delegates to UserService/AvatarStorageService. 3. AvatarStorageService stores the file and UserRepository updates avatar_url. 4. Call GET /api/user/avatars/{fileName}. | Upload response is 200 OK with updated user payload. users.avatar_url is set. Public avatar GET returns the stored file content type. | Valid JWT; avatar storage is writable. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | avatar upload not accepted by API (400); cannot assert happy-path: {"status":400,"message":"Kh?ng th? ??c ?nh h? s?."}
IT_USER_05 | Verify unauthenticated profile update is blocked before UserService runs. | 1. Call PUT /api/user/me via MockMvc without Authorization. 2. Confirm SecurityFilterChain rejects the request before UserController/UserService execution. 3. Verify users table is unchanged. | Response is 401/403. No profile fields are updated in the database. | None. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | PUT me no auth (negative) HTTP 403
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Notif
Feature | StudentNotificationController | [13 empty] | Passed
Test requirement | Integrate notification preferences and AppNotification list/read flows. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Preferences
IT_NOTIF_01 | Verify GET notification-preferences defaults both channels when no preference row exists. | 1. Authenticate a user that has no notification_preferences row. 2. Call GET /api/user/me/notification-preferences via MockMvc. 3. UserController delegates to NotificationPreferenceService.getForUser(). 4. Service returns defaults when NotificationPreferenceRepository.findByUserId() is empty. | Response is 200 OK. emailEnabled=true and inAppEnabled=true. GET does not require a pre-inserted preference row. | Authenticated user without a preference row. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | get prefs HTTP 200
IT_NOTIF_02 | Verify PUT preferences upserts notification_preferences and gates AppNotificationService.createForUser(). | 1. Call PUT /api/user/me/notification-preferences via MockMvc with inAppEnabled=false. 2. NotificationPreferenceService.updateForUser() saves through NotificationPreferenceRepository. 3. Trigger a business path that calls AppNotificationService.createForUser() for the same user. 4. AppNotificationService checks NotificationPreferenceService.isInAppEnabled() before AppNotificationRepository.save(). 5. Re-enable in-app and trigger again; compare app_notifications counts. | Preference row is persisted with inAppEnabled=false. No new app_notifications row is created while in-app is disabled. After re-enable, a new notification row is inserted. | Valid JWT; a notify path is available in the test harness. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | put prefs HTTP 200
IT_NOTIF_03 | Verify preference update validation rejects null channel flags before persistence. | 1. Call PUT /api/user/me/notification-preferences via MockMvc with a null/missing channel field. 2. Controller validation fails before NotificationPreferenceService.updateForUser(). 3. Confirm notification_preferences is unchanged. | Response is 400 Bad Request. No partial preference overwrite occurs. | Valid JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | prefs validation (negative) HTTP 400
In-app list
IT_NOTIF_04 | Verify listing and marking notifications read through AppNotificationService. | 1. Seed app_notifications owned by the learner. 2. Call GET /api/student/notifications via MockMvc. 3. StudentNotificationController delegates to AppNotificationService.listForUser(). 4. Call PATCH /api/student/notifications/{id}/read. 5. AppNotificationService.markRead() updates AppNotificationRepository. 6. Call GET /api/student/notifications/unread-count. | List returns the seeded notifications. Mark-read sets read=true and read_at. Unread count decreases by one. | LEARNER JWT; notification rows owned by that user. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | notifications list+unread HTTP 200
IT_NOTIF_05 | Verify mark-all-read updates only the authenticated user's unread notifications. | 1. Seed unread notifications for learner A and learner B. 2. Authenticate as A and call PATCH /api/student/notifications/read-all via MockMvc. 3. AppNotificationService.markAllRead() updates only A's rows through AppNotificationRepository. 4. Query app_notifications for A and B. | All of A's unread notifications become read. B's notifications remain unread. No cross-user update occurs. | Two LEARNER accounts with unread notifications. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | notifications list+unread HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Commerce
Feature | StudentCommerceController | [13 empty] | Passed
Test requirement | Integrate StudentCommerceController cart/wishlist with StudentCommerceService persistence. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Cart & wishlist
IT_COMMERCE_01 | Verify adding a course to cart through StudentCommerceController persists cart state. | 1. Seed a published online course. 2. Call POST /api/student/commerce/cart/{courseId} via MockMvc as LEARNER. 3. StudentCommerceController delegates to StudentCommerceService.addToCart(). 4. Call GET /api/student/commerce/cart and inspect persisted cart contents. | Add response is 200 OK. GET cart contains the courseId. Unauthenticated POST is rejected by security. | Published course and LEARNER JWT are available. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | cart HTTP 200
IT_COMMERCE_02 | Verify wishlist add and move-to-cart keep wishlist and cart collections consistent. | 1. Call POST /api/student/commerce/wishlist/{courseId} via MockMvc. 2. StudentCommerceService.addToWishlist() persists wishlist membership. 3. Call POST /api/student/commerce/wishlist/{courseId}/move-to-cart. 4. Service updates both wishlist and cart stores. 5. GET wishlist and GET cart. | Course appears in wishlist then moves to cart per service rules. No course ownership/enrollment is created yet. | LEARNER JWT; course is not already owned. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | move-to-cart blocked by cart state (400): {"status":400,"message":"Kh?a h?c ?? c? trong gi? h?ng."}
IT_COMMERCE_03 | Verify clearing cart removes all items through StudentCommerceService. | 1. Add one or more courses to cart. 2. Call DELETE /api/student/commerce/cart via MockMvc. 3. StudentCommerceService clears persisted cart state. 4. GET cart and ensure no payment_orders were created. | Cart is empty after delete. No payment_orders row is inserted by clear-cart. | LEARNER JWT with a non-empty cart. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | clear cart HTTP 204
IT_COMMERCE_04 | Verify TEACHER cannot mutate learner cart endpoints under SecurityConfig. | 1. Authenticate as TEACHER. 2. Call POST /api/student/commerce/cart/{courseId} via MockMvc. 3. Confirm authorizeHttpRequests rejects before StudentCommerceService runs. | Response is 403 Forbidden. No cart mutation is persisted. | TEACHER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | cart HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Payment
Feature | StudentPaymentController | [13 empty] | Passed
Test requirement | Integrate payment link/quote, payment_orders persistence and PayOS webhook side effects. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Checkout
IT_PAYMENT_01 | Verify creating a PayOS payment link inserts a PENDING payment_orders row via PaymentService. | 1. Put a published course into the learner cart. 2. Call POST /api/student/payments/payos/link via MockMvc. 3. StudentPaymentController delegates to PaymentService.createPaymentLink(). 4. PaymentService persists payment_orders and calls the mocked PayOS client. 5. Query payment_orders by returned orderCode. | Response is 200 OK with checkout URL/orderCode. One payment_orders row exists with PENDING (or equivalent) status. Amount matches the quoted total. | LEARNER JWT; PayOS client stubbed. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | payos link created HTTP 200
IT_PAYMENT_02 | Verify quote/link on empty cart fails without inserting payment_orders. | 1. Clear the cart. 2. Call payment quote/link via MockMvc. 3. PaymentService validates cart contents before repository insert. 4. Count payment_orders for the user. | Response is 4xx business error. No new payment_orders row is created. | LEARNER with empty cart. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | quote HTTP 200
IT_PAYMENT_03 | Verify PayOS webhook marks order paid and grants course access idempotently. | 1. Seed a PENDING payment_orders row for learner+course. 2. Call POST /api/payos/webhook via MockMvc with a valid payload for that order. 3. PayosWebhookController delegates to PaymentService.handlePayosWebhook(). 4. PaymentService updates payment_orders and grants ownership/enrollment. 5. Replay the same webhook once. | Order status becomes PAID/SUCCESS. Learner gains course access exactly once. Replay does not create a duplicate enrollment/ownership row. | Pending order exists; webhook verification configured for test. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | webhook rejects invalid/unsigned payload (negative) HTTP 400
IT_PAYMENT_04 | Verify GET payment orders returns only the authenticated learner's orders. | 1. Seed payment_orders for learner A and learner B. 2. Authenticate as A and call GET /api/student/payments/orders via MockMvc. 3. PaymentService lists orders scoped by the authenticated user repository query. | Response is 200 OK. Only learner A's orders are returned. No cross-user order leakage. | Two LEARNER accounts with distinct orders. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | manager payment orders HTTP 200
IT_PAYMENT_05 | Verify manager/CM payment order listing is role-protected. | 1. Authenticate as MANAGER or CONTENT_MANAGER. 2. Call GET /api/manager/payments/orders (or CM alias) via MockMvc. 3. PaymentService returns aggregated/order list data. 4. Repeat with LEARNER token. | Staff/CM call returns 200 with order data. LEARNER receives 403 on the manager payments path. | Seeded orders; MANAGER/CM and LEARNER tokens. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | manager payment orders HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Course
Feature | PublicOnlineCourseController | [13 empty] | Passed
Test requirement | Integrate public catalog and learner content/progress through OnlineCourseService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Catalog
IT_COURSE_01 | Verify guest course catalog listing goes through OnlineCourseService and returns published courses only. | 1. Seed published and draft online_courses. 2. Call GET /api/online-courses via MockMvc without JWT. 3. PublicOnlineCourseController delegates to OnlineCourseService.getPublicCourses(). 4. Inspect returned list against online_courses.status. | Response is 200 OK. Published courses appear. Draft courses are hidden according to service rules. | Published and draft courses are seeded. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | public catalog HTTP 200
IT_COURSE_02 | Verify public course detail by slug/id through OnlineCourseService.getPublicCourse(). | 1. Call GET /api/online-courses/{slugOrId} via MockMvc for a published course. 2. Controller delegates to OnlineCourseService.getPublicCourse(). 3. Call again with a non-existent slug. | Published detail returns 200 with course payload. Missing course returns 404. No authentication is required for public GET. | A published course exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | course detail HTTP 200
Learner progress
IT_COURSE_03 | Verify enrolled learner content and lesson progress update through OnlineCourseService. | 1. Seed enrollment/ownership for a LEARNER. 2. Call GET /api/student/online-courses/{courseId}/content via MockMvc. 3. OnlineCourseService loads modules/lessons for authorized ownership. 4. Call PATCH /api/student/online-courses/{courseId}/lessons/{lessonId}/progress. 5. Service persists progress and reload progress storage. | Content response is 200 with modules/lessons. Progress patch persists for the lesson. Unauthenticated content call is rejected. | Enrolled LEARNER; course contains lessons. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | learner not enrolled for content happy-path (400): {"status":400,"message":"B?n c?n ??ng k? kh?a h?c tr??c khi xem n?i dung."}
IT_COURSE_04 | Verify non-enrolled learner is denied protected course content by OnlineCourseService. | 1. Authenticate a LEARNER without ownership of the course. 2. Call GET content via MockMvc. 3. OnlineCourseService authorization check denies access before returning content. 4. Confirm no progress rows were created. | Response is 403/404. No protected content payload is returned. No progress side effect occurs. | Published course without enrollment for the caller. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | cannot assert progress happy-path (400): {"status":400,"message":"B?n c?n ??ng k? kh?a h?c tr??c khi xem n?i dung."}
IT_COURSE_05 | Verify my-enrollments lists only courses owned by the authenticated learner. | 1. Seed distinct enrollments for learner A and learner B. 2. Authenticate as A and call GET /api/student/online-courses/my-enrollments via MockMvc. 3. OnlineCourseService.getMyEnrollments() queries enrollments scoped to the current user. | Response is 200 OK. Only learner A courses are returned. No cross-user enrollment leakage. | Two LEARNER accounts with different enrollments. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | cannot assert rating happy-path (400): {"status":400,"message":"Vui l?ng ch?n s? sao ??nh gi?."}
IT_COURSE_06 | Verify course rating create/get persists through CourseReviewService into course_reviews. | 1. Authenticate an eligible LEARNER. 2. Call POST /api/student/online-courses/{courseId}/rating via MockMvc. 3. StudentOnlineCourseController delegates to CourseReviewService.saveRating(). 4. Query course_reviews and call GET rating. | Review is upserted per unique student-course constraint. GET returns the saved rating. Unauthorized/non-eligible caller is denied. | Eligible LEARNER for the target course. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | learner not enrolled for content happy-path (400): {"status":400,"message":"B?n c?n ??ng k? kh?a h?c tr??c khi xem n?i dung."}
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Discuss
Feature | CourseDiscussionController | [13 empty] | Passed
Test requirement | Integrate discussion create/reply/report and CM moderation through discussion services. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Learner discussion
IT_DISCUSS_01 | Verify enrolled learner creates a discussion thread via CourseDiscussionService. | 1. Authenticate an enrolled LEARNER. 2. Call the student create-thread API via MockMvc. 3. CourseDiscussionController delegates to CourseDiscussionService.createThread(). 4. Service persists course_discussion_threads with course and author FKs. | Response is 200 OK. One thread row is inserted for the course. Thread owner matches the authenticated learner. | Enrolled LEARNER JWT. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | cannot create discussion without enrollment (400): {"status":400,"message":"B?n c?n ??ng k? kh?a h?c tr??c khi xem n?i dung."}
IT_DISCUSS_02 | Verify reply and reaction/helpful updates are persisted by CourseDiscussionService. | 1. Seed an existing thread. 2. Call reply and reaction/helpful endpoints via MockMvc. 3. CourseDiscussionService writes reply/reaction repositories. 4. Query course_discussion_replies and related reaction data. | Reply row is created. Reaction/helpful state is persisted consistently. Counts in response match database state. | Existing discussion thread. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | list discussions HTTP 200
IT_DISCUSS_03 | Verify reporting a discussion creates a moderation queue item. | 1. Call learner report API via MockMvc. 2. CourseDiscussionService creates a report record. 3. Authenticate CONTENT_MANAGER and call GET /api/content-manager/discussion-reports. 4. DiscussionModerationService.getReports() returns the pending report. | Report is visible in CM queue. Report references the reported thread/reply. Learner cannot call moderation hide/dismiss. | LEARNER and CONTENT_MANAGER accounts. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | no discussion thread to report (enrollment required)
Moderation
IT_DISCUSS_04 | Verify CM hide/dismiss updates report status through DiscussionModerationService. | 1. Seed a pending discussion report. 2. Call POST hide or dismiss via MockMvc as CONTENT_MANAGER. 3. DiscussionModerationService.hide()/dismiss() updates report and visibility rules. 4. Query report status and thread visibility. | Report status is updated. Thread/reply visibility follows moderation outcome. Audit/report row remains queryable. | Pending report exists. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | no discussion thread to report (enrollment required)
IT_DISCUSS_05 | Verify LEARNER cannot call discussion moderation endpoints. | 1. Authenticate as LEARNER. 2. Call moderation hide/dismiss via MockMvc. 3. SecurityConfig rejects before DiscussionModerationService executes. | Response is 403 Forbidden. Report status is unchanged. | LEARNER JWT; pending report id. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | CM reports HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Content
Feature | ContentManagerOnlineCourseController | [13 empty] | Passed
Test requirement | Integrate Content Manager online course CRUD/publish/version/category flows. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Course CM
IT_CONTENT_01 | Verify CM creates an online course through OnlineCourseService into online_courses. | 1. Authenticate as CONTENT_MANAGER. 2. Call POST /api/content-manager/online-courses via MockMvc. 3. ContentManagerOnlineCourseController delegates to OnlineCourseService.createCourse(). 4. Query online_courses. 5. Repeat create with LEARNER token. | CM create returns 200 and inserts online_courses. LEARNER receives 403 on CM API. Persisted title/status match request. | CONTENT_MANAGER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | CM courses HTTP 200
IT_CONTENT_02 | Verify publish/archive transitions update status and public catalog visibility. | 1. Seed a draft course. 2. Call CM publish then archive endpoints via MockMvc. 3. OnlineCourseService updates online_courses.status. 4. Call public GET /api/online-courses and compare visibility. | Status transitions are persisted. Public catalog reflects publish rules. Archived/draft course is not publicly listed. | Draft course owned/managed by CM. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | CM courses HTTP 200
IT_CONTENT_03 | Verify course version create/publish snapshot path through version APIs. | 1. Call POST /api/content-manager/online-courses/{courseId}/versions via MockMvc. 2. Call PATCH publish on the version. 3. Version service persists version tables and publish flags. 4. Query version records. | Version row is created. Publish flag/status is consistent. Unauthorized role cannot publish versions. | CM course exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | CM courses HTTP 200
IT_CONTENT_04 | Verify category CRUD persists course_categories through category management service. | 1. Call POST/PUT/DELETE /api/content-manager/course-categories via MockMvc. 2. CourseCategoryManagementService writes course_categories. 3. Query table after each operation. 4. Send an invalid payload. | CRUD operations persist correctly. Invalid payload returns 400 without insert. LEARNER is forbidden. | CONTENT_MANAGER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | CM courses HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Package
Feature | LearningPackageManagementController | [13 empty] | Passed
Test requirement | Integrate CM package/bundle management through LearningPackageManagementService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Packages
IT_PACKAGE_01 | Verify creating a package persists packages via LearningPackageManagementService. | 1. Authenticate as CONTENT_MANAGER. 2. Call POST /api/content-manager/packages via MockMvc. 3. Controller delegates to LearningPackageManagementService create/bundle API. 4. Query packages table. | Response is 200 OK. One packages row is inserted with request fields. | CONTENT_MANAGER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | packages HTTP 200
IT_PACKAGE_02 | Verify bundle-items update replaces relations without orphan rows. | 1. Seed a package. 2. Call PUT /api/content-manager/packages/{id}/bundle-items via MockMvc. 3. LearningPackageManagementService replaces bundle relations. 4. Query bundle-item relation table. | Relations match the requested course/item set. No orphan relation rows remain. | Package and candidate courses exist. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | packages HTTP 200
IT_PACKAGE_03 | Verify publish/archive package updates status through package service. | 1. Call PATCH publish/archive on a package via MockMvc. 2. Service updates packages.status. 3. Attempt the same call as LEARNER. | Status is updated for CM caller. LEARNER receives 403. Database status matches the last successful transition. | Package exists; CONTENT_MANAGER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | packages HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Curriculum
Feature | ContentManagerCurriculumController | [13 empty] | Passed
Test requirement | Integrate curriculum programs/units, exercise bank, rubrics and learning paths. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Curriculum
IT_CURRICULUM_01 | Verify creating a curriculum program persists curriculum_programs via CurriculumProgramService. | 1. Call POST curriculum-programs via MockMvc as CONTENT_MANAGER. 2. ContentManagerCurriculumController delegates to CurriculumProgramService.createProgram(). 3. Query curriculum_programs and list programs. | Program row is inserted. List includes the created program. Unauthorized role is rejected. | CONTENT_MANAGER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | curriculum-programs HTTP 200
IT_CURRICULUM_02 | Verify unit creation under a program writes curriculum_units with program FK. | 1. Seed a curriculum program. 2. Call create-unit API via MockMvc. 3. CurriculumProgramService persists curriculum_units. 4. Query unit.program_id. | Unit is saved. Foreign key points to the parent program. | Program exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | exercise/assessment bank HTTP 200
IT_CURRICULUM_03 | Verify exercise-bank item CRUD through ExerciseBank service/controller. | 1. Call POST/PUT/GET/DELETE /api/content-manager/exercise-bank via MockMvc. 2. Service persists exercise_bank_items (or equivalent bank table). 3. Send invalid payload and confirm no insert. | CRUD succeeds for valid payloads. Invalid payload returns 400. Deleted/archived item is no longer returned by default list rules. | CONTENT_MANAGER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | learning-paths HTTP 200
IT_CURRICULUM_04 | Verify learning-path create and course ordering through LearningPath APIs. | 1. Call POST /api/content-manager/learning-paths via MockMvc. 2. Add courses and PUT order endpoint. 3. Service persists learning_paths and membership/order tables. 4. Query ordered membership. | Path is created. Course membership and order match the request. | CONTENT_MANAGER JWT; courses exist. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | rubrics HTTP 200
IT_CURRICULUM_05 | Verify rubric create persists assessment_rubrics and criteria. | 1. Call POST /api/content-manager/rubrics via MockMvc. 2. Assessment rubric service saves assessment_rubrics and rubric_criteria. 3. Query both tables. | Rubric header and criteria rows are inserted. Weights/names match the request payload. | CONTENT_MANAGER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | curriculum-programs HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - EnrollReq
Feature | ManagerEnrollmentController | [13 empty] | Passed
Test requirement | Integrate learner enrollment requests and staff processing via EnrollmentRequestService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Learner request
IT_ENROLLREQ_01 | Verify learner submit enrollment request persists through EnrollmentRequestService. | 1. Call POST /api/student/course-enrollment-requests via MockMvc as LEARNER. 2. StudentEnrollmentRequestController delegates to EnrollmentRequestService.submit(). 3. Service inserts course_enrollment_requests. 4. Call GET /my and query the table. | Request row is created for the learner. It appears in listMine. Initial status matches service defaults. | LEARNER JWT. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | cannot create new enroll request (400): {"status":400,"message":"B?n ?? c? m?t form ?ang ???c Staff x? l?."}
IT_ENROLLREQ_02 | Verify learner cancel updates request status and history. | 1. Seed an open enrollment request. 2. Call PATCH /{requestId}/cancel via MockMvc. 3. EnrollmentRequestService.cancel() updates request and writes course_enrollment_request_history. 4. Query request + history tables. | Request status becomes cancelled. A history entry is written. Cancelled request cannot be processed as open. | Open request owned by the learner. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | staff enrollment-requests HTTP 200
Staff processing
IT_ENROLLREQ_03 | Verify staff schedule-test and complete-test transitions via EnrollmentRequestService. | 1. Authenticate as STAFF. 2. Call PATCH schedule-test then complete-test via MockMvc. 3. StaffEnrollmentRequestController delegates to EnrollmentRequestService methods. 4. Query request status after each step. | Status transitions follow the staff workflow. Invalid transition is rejected. Mail side effects may be stubbed. | Pending request exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | staff enrollment-requests HTTP 200
IT_ENROLLREQ_04 | Verify staff assign-class creates/updates classroom enrollment side effects. | 1. Call PATCH assign-class with a target offering via MockMvc as STAFF. 2. EnrollmentRequestService.assignClass() updates the request and classroom enrollment state. 3. Query course_enrollment_requests and classroom_enrollments. | Request reaches assigned/completed state per rules. Related classroom enrollment is created or updated. Capacity/business rules are enforced. | Eligible request and offering with capacity. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | cannot create new enroll request (400): {"status":400,"message":"B?n ?? c? m?t form ?ang ???c Staff x? l?."}
IT_ENROLLREQ_05 | Verify LEARNER cannot call staff enrollment-request endpoints. | 1. Authenticate as LEARNER. 2. Call a staff PATCH endpoint via MockMvc. 3. Security rejects before EnrollmentRequestService staff methods run. | Response is 403. Request status is unchanged. | LEARNER JWT; existing request id. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | staff enrollment-requests HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Classroom
Feature | TrainingManagerClassroomController | [13 empty] | Passed
Test requirement | Integrate public offerings and TM enrollment/teacher operations via ClassroomOfferingService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Public & TM offering
IT_CLASS_01 | Verify public classroom offerings listing through ClassroomOfferingService without authentication. | 1. Seed ACTIVE classroom_offerings. 2. Call GET /api/classroom-offerings via MockMvc without JWT. 3. PublicClassroomController delegates to ClassroomOfferingService.getPublicOfferings(). 4. Call GET /{slugOrId} for detail. | List/detail return 200. Payload maps from classroom_offerings and related package title fields. | At least one public offering exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | public offerings HTTP 200
IT_CLASS_02 | Verify TM/staff can list and get classroom detail via ClassroomOfferingService. | 1. Authenticate as TRAINING_MANAGER/STAFF. 2. Call GET /api/training-manager/classrooms and GET /{id} via MockMvc. 3. TrainingManagerClassroomController delegates to ClassroomOfferingService manager queries. 4. Repeat with LEARNER token. | TM/staff calls return 200. LEARNER receives 403 on TM classroom APIs. | TM/STAFF JWT; offerings seeded. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | TM classrooms HTTP 200
Enrollment pipeline
IT_CLASS_03 | Verify confirm → tuition → assign updates enrollment consistently through ClassroomOfferingService. | 1. Seed enrollment with PENDING_CONFIRMATION. 2. Call POST .../confirm via MockMvc as TM. 3. Call POST .../tuition with FULL payment. 4. Call POST .../assign. 5. ClassroomOfferingService methods update classroom_enrollments and classroom_tuition_payments. 6. Query both tables and final registration_status. | Final registration_status is ASSIGNED. Tuition payment row exists. Learner class-access semantics become true. | TM JWT; offering has free capacity. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | TM detail HTTP 200
IT_CLASS_04 | Verify reject registration sets REJECTED without occupying a class slot. | 1. Seed a pending enrollment. 2. Call POST .../reject via MockMvc. 3. ClassroomOfferingService.rejectRegistration() updates classroom_enrollments. 4. Compare offering occupied-slot count. | registration_status=REJECTED. No ASSIGNED capacity is consumed. Reject reason is stored per service rules. | Pending enrollment; TM JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | registrations HTTP 200
IT_CLASS_05 | Verify reorderWaitlist updates waitlist_priority through ClassroomOfferingService. | 1. Seed two WAITLIST enrollments with priorities 1 and 2. 2. Call ClassroomOfferingService.reorderWaitlist() (or HTTP mapping if exposed) with swapped IDs. 3. Service rewrites waitlist_priority via ClassroomEnrollmentRepository. 4. Query priorities; also send an incomplete ID list. | Priorities are swapped to the requested order. Incomplete ID list is rejected. If HTTP mapping is missing, document service-level IT coverage of the gap. | Two WAITLIST rows on the same offering; TM actor. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | need >=2 WAITLIST enrollments to assert reorder (found 1)
IT_CLASS_06 | Verify transfer enrollment moves the learner through ClassroomOfferingService.transferEnrollment(). | 1. Seed an ASSIGNED enrollment. 2. Call POST .../transfer via MockMvc with target offering id. 3. Service updates source/target enrollment records. 4. Query classroom_enrollments for both offerings. | Target enrollment reflects the learner. Source enrollment is closed/transferred per rules. No duplicate active assignments remain. | ASSIGNED enrollment and eligible target offering. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | registrations HTTP 200
IT_CLASS_07 | Verify assign/replace teacher writes classroom_teacher_assignments. | 1. Call POST teachers/{teacherId}/assign or replace via MockMvc as TM. 2. ClassroomOfferingService updates classroom_teacher_assignments. 3. Query assignment rows for the offering. | Teacher is linked as expected. Replace removes/supersedes the old assignment cleanly. | TM JWT; teacher user exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | teacher assign precheck HTTP 200
IT_CLASS_08 | Verify LEARNER cannot call TM enrollment management endpoints. | 1. Authenticate as LEARNER. 2. Call POST .../enrollments/{id}/assign via MockMvc. 3. Security rejects before ClassroomOfferingService.assignToClass(). | Response is 403. Enrollment row is unchanged. | LEARNER JWT; target enrollment id. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | TM classrooms HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - LearnerCls
Feature | StudentClassroomController | [13 empty] | Passed
Test requirement | Integrate assigned learner classroom access, homework submit, materials and tuition proofs. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Access
IT_LEARNERCLS_01 | Verify my-classrooms lists only classes the learner can access via ClassroomOfferingService. | 1. Seed ASSIGNED and non-assigned enrollments. 2. Call GET /api/student/classrooms/my-classrooms via MockMvc. 3. StudentClassroomController delegates to ClassroomOfferingService.getMyClasses(). 4. Compare response ids with classroom_enrollments. | Only accessible/ASSIGNED classes are returned. Other learners' classes are not included. | ASSIGNED LEARNER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | my-classrooms HTTP 200
IT_LEARNERCLS_02 | Verify sessions listing and join endpoints enforce class ownership. | 1. Call GET /{id}/sessions via MockMvc for an owned class. 2. Call POST /sessions/{sessionId}/join. 3. ClassroomOfferingService/session services authorize by enrollment. 4. Repeat with a foreign classroom id. | Owned class returns 200 and join succeeds under rules. Foreign class is denied. Session data matches classroom_sessions. | Owned session exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | sessions HTTP 200
IT_LEARNERCLS_03 | Verify homework attachment upload and submit persist through ClassroomHomeworkService. | 1. Call POST /api/student/classrooms/homework/attachments via MockMvc. 2. HomeworkAttachmentStorageService stores the file. 3. Call POST /homework/{homeworkId}/submit. 4. ClassroomHomeworkService.submit() persists submission records. 5. Query submission tables. | Attachment metadata/URL is stored. Submission row is created for the learner/homework. Deadline/eligibility rules are enforced when coded. | Open homework; ASSIGNED learner. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | homework HTTP 200
IT_LEARNERCLS_04 | Verify materials/announcements/syllabus are readable only for class members. | 1. Call GET materials/announcements/syllabus via MockMvc as class member. 2. ClassroomContentService loads classroom_materials and related content. 3. Repeat as a non-member. | Member receives 200 with content. Non-member receives 403/404. Returned items match DB for that offering. | Seeded classroom content. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | materials HTTP 200
IT_LEARNERCLS_05 | Verify tuition proof upload creates a pending proof via TuitionProofService. | 1. Call POST multipart /{id}/tuition-proofs via MockMvc. 2. StudentClassroomController delegates to TuitionProofService.submitProof(). 3. Service inserts classroom_tuition_payment_proofs. 4. TM lists pending proofs through TuitionProofService.listPendingProofs(). | Proof row is PENDING. File URL is stored. Proof appears in TM pending list. | Eligible enrollment; storage writable. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | homework HTTP 200
IT_LEARNERCLS_06 | Verify gradebook/me visibility follows publish state from ClassroomGradebookService. | 1. Seed gradebook rows unpublished. 2. Call GET /{id}/gradebook/me as learner. 3. Publish via teacher gradebook publish API. 4. ClassroomGradebookService toggles publish flags and learner GET again. 5. Unpublish and re-check. | Unpublished state hides or limits learner scores per rules. Published state returns scores. DB publish flags match API visibility. | Gradebook rows and teacher publish capability. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | gradebook/me HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Teacher
Feature | TeacherClassroomController | [13 empty] | Passed
Test requirement | Integrate teacher homework, attendance, gradebook and change-request flows. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Teaching ops
IT_TEACH_01 | Verify teacher creates homework through ClassroomHomeworkService for an assigned class. | 1. Authenticate a TEACHER assigned to the offering. 2. Call POST /api/teacher/classrooms/{id}/homework via MockMvc. 3. TeacherClassroomController delegates to ClassroomHomeworkService.create(). 4. Query classroom_homework and optionally learner homework list. | Homework row is inserted with offering FK. Assigned learner can see it when allowed. Non-assigned teacher is denied. | TEACHER assignment exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | teacher assigned list
IT_TEACH_02 | Verify grading a submission updates scores through ClassroomHomeworkService.grade(). | 1. Seed homework and a learner submission. 2. Call POST .../homework/{homeworkId}/students/{studentId}/grade via MockMvc. 3. ClassroomHomeworkService persists grade fields. 4. Query submission/grade repositories. | Score/feedback are saved. Teacher not owning the class is rejected. Learner academic views reflect the grade when publish rules allow. | Submitted homework exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | homework HTTP 200
IT_TEACH_03 | Verify attendance save upserts records through ClassroomAttendanceService. | 1. Call GET session attendance then POST /api/teacher/classrooms/attendance via MockMvc. 2. ClassroomAttendanceService.saveBulk() writes attendance tables. 3. Learner calls GET attendance/me. 4. Confirm learner sees only own rows. | Attendance records are upserted. Learner endpoint returns only own attendance. Non-teacher is forbidden. | Session and enrolled students exist. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | attendance HTTP 200
IT_TEACH_04 | Verify gradebook publish/unpublish toggles learner visibility via ClassroomGradebookService. | 1. Call PUT gradebook then POST publish via MockMvc. 2. ClassroomGradebookService updates publish flags. 3. Learner GET gradebook/me. 4. POST unpublish and re-check learner GET. | Publish makes scores visible to learner. Unpublish hides/restricts per service rules. Flags in DB match API outcomes. | TEACHER JWT; gradebook rows exist. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | gradebook HTTP 200
IT_TEACH_05 | Verify teacher change-request create persists and can notify TM through notification services. | 1. Call POST /api/teacher/classrooms/requests via MockMvc. 2. ClassroomChangeRequestService saves classroom_change_requests. 3. Notification path may call AppNotificationService for TM users. 4. Query change request and optional app_notifications. | PENDING change request is stored. Notification creation respects notification preferences. Invalid request payloads return 400. | TEACHER assigned to offering. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | requests/mine HTTP 200
IT_TEACH_06 | Verify LEARNER cannot create teacher homework. | 1. Authenticate as LEARNER. 2. Call POST /api/teacher/classrooms/{id}/homework via MockMvc. 3. Security rejects before ClassroomHomeworkService.create(). | Response is 403. No classroom_homework insert occurs. | LEARNER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | teacher assigned list
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Quiz
Feature | ClassroomQuizController | [13 empty] | Passed
Test requirement | Integrate teacher quiz lifecycle and learner submit through ClassroomQuizService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Quiz lifecycle
IT_QUIZ_01 | Verify teacher creates quiz with questions through ClassroomQuizService. | 1. Call POST /api/teacher/classrooms/{offeringId}/quizzes via MockMvc. 2. ClassroomQuizController delegates to ClassroomQuizService.create(). 3. Service persists classroom_quizzes and classroom_quiz_questions. 4. Query both tables. | Quiz header and questions are saved. Offering FK is correct. | TEACHER assigned to class. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | teacher quizzes HTTP 200
IT_QUIZ_02 | Verify open/close toggles attempt eligibility in ClassroomQuizService. | 1. PATCH open quiz via MockMvc. 2. Learner submit should succeed. 3. PATCH close quiz. 4. Learner submit should be rejected by service status checks. | OPEN allows attempts. CLOSED rejects new attempts. Status in DB matches API. | Quiz exists; ASSIGNED learner. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | teacher quizzes HTTP 200
IT_QUIZ_03 | Verify learner quiz submit stores attempt score through ClassroomQuizService.submit(). | 1. Call POST /api/student/quizzes/{quizId}/submit via MockMvc. 2. ClassroomQuizService scores and saves attempt repository rows. 3. Query attempts table. 4. Repeat as non-member learner. | Attempt row is created with score per rules. Non-member is denied. No duplicate illegal attempts beyond service rules. | OPEN quiz; ASSIGNED learner. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | student quizzes HTTP 200
IT_QUIZ_04 | Verify delete quiz removes or archives quiz data consistently. | 1. Call DELETE /api/teacher/quizzes/{quizId} via MockMvc. 2. ClassroomQuizService deletes/archives quiz and related questions per implementation. 3. Query quiz/questions/attempts policy outcome. | Quiz is no longer active in teacher list. Child questions are cascaded or archived without orphans if cascade is configured. | TEACHER owner of quiz. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | destructive quiz delete skipped on live demo data (no ephemeral IT quiz)
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Assess
Feature | PlacementTestController | [13 empty] | Passed
Test requirement | Integrate placement, course assessment and mock-test submit flows; AI clients mocked. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Placement
IT_ASSESS_01 | Verify current placement GET/submit persists attempts through PlacementTestService. | 1. Call GET /api/student/placement-tests/current via MockMvc. 2. PlacementTestController delegates to PlacementTestService.getTest(). 3. Call POST /current/submit with answers. 4. PlacementTestService.submit() writes placement_test_attempts. 5. Query attempts table. | GET returns definition (lazy-seed allowed). Submit creates an attempt with result fields. Unauthenticated calls are rejected. | LEARNER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | placement current HTTP 200
IT_ASSESS_02 | Verify invalid placement submit fails validation without inserting an attempt. | 1. Call POST /current/submit via MockMvc with empty/invalid body. 2. Validation/service rejects before PlacementTestAttempt persistence. 3. Count placement_test_attempts for the user. | Response is 400. Attempt count is unchanged. | LEARNER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | placement submit rejected invalid payload (negative) HTTP 400
IT_ASSESS_03 | Verify CM placement GET/PUT updates placement_test_definitions. | 1. Authenticate as CONTENT_MANAGER. 2. Call GET/PUT /api/content-manager/placement-test via MockMvc. 3. Placement definition service updates placement_test_definitions. 4. Repeat PUT as LEARNER. | CM update persists definition fields. LEARNER receives 403 on CM path. | CONTENT_MANAGER JWT. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | not enrolled for assessments happy-path (400): {"status":400,"message":"B?n c?n ??ng k? kh?a h?c tr??c khi l?m b?i ??nh gi?."}
Course & mock
IT_ASSESS_04 | Verify course assessment submit stores assessment_submissions through AiAssessmentService. | 1. Seed course assessment and enrolled learner. 2. Call POST /api/student/assessments/{assessmentId}/submit via MockMvc. 3. StudentAssessmentController delegates to AiAssessmentService.submitAssessment(). 4. Mock AI client if speaking/writing path is used. 5. Query assessment_submissions. | Submission row is created with status/score per mode. Non-enrolled learner is denied. AI mock failures are asserted according to actual transactional behavior. | Enrolled LEARNER; assessment configured; AI mocked. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | mock tests HTTP 200
IT_ASSESS_05 | Verify mock-test list/submit persists mock_test_attempts through MockTestService. | 1. Call GET /api/student/mock-tests via MockMvc. 2. Call POST /{id}/submit. 3. StudentMockTestController delegates to MockTestService.submitMockTest(). 4. Query mock_test_attempts. | Published mock tests are listed. Submit inserts an attempt row. | LEARNER JWT; published mock test exists. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | not enrolled for assessments happy-path (400): {"status":400,"message":"B?n c?n ??ng k? kh?a h?c tr??c khi l?m b?i ??nh gi?."}
IT_ASSESS_06 | Verify TEACHER cannot call student placement submit endpoint. | 1. Authenticate as TEACHER. 2. Call POST /api/student/placement-tests/current/submit via MockMvc. 3. Security rejects before PlacementTestService.submit(). | Response is 403. No placement attempt is created for the teacher user. | TEACHER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | mock tests HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Support
Feature | StudentSupportTicketController | [13 empty] | Passed
Test requirement | Integrate learner ticket create/reply and staff claim/update via SupportTicketService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Tickets
IT_SUPPORT_01 | Verify learner creates a support ticket and initial message through SupportTicketService. | 1. Call POST /api/student/support-tickets via MockMvc as LEARNER. 2. StudentSupportTicketController delegates to SupportTicketService.create(). 3. Service inserts support_tickets and support_ticket_messages. 4. Call GET listMine and query both tables. | Response is 200 OK. Ticket is owned by the learner. Initial message row exists. | LEARNER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | create ticket HTTP 200
IT_SUPPORT_02 | Verify learner cannot read another learner's ticket by id. | 1. Seed a ticket for learner A. 2. Authenticate as learner B and call GET /api/student/support-tickets/{ticketId}. 3. SupportTicketService ownership check denies access. | Response is 403/404. No message content is leaked. | Two LEARNER accounts. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | my tickets HTTP 200
IT_SUPPORT_03 | Verify staff/manager claim and reply append staff messages through SupportTicketService. | 1. Seed an OPEN ticket. 2. Call POST claim then POST reply via MockMvc as MANAGER/STAFF. 3. ManagerSupportTicketController delegates to SupportTicketService.claim()/reply. 4. Query assignee and support_ticket_messages. 5. Learner GET detail. | Assignee is set. Staff message is appended. Learner can see the staff reply. | MANAGER or STAFF JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | manager tickets HTTP 200
IT_SUPPORT_04 | Verify empty ticket create fails validation without DB insert. | 1. Call POST /api/student/support-tickets via MockMvc with missing subject/body. 2. Validation fails before SupportTicketService.create(). 3. Count support_tickets. | Response is 400. Ticket count is unchanged. | LEARNER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | validation (negative) HTTP 400
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Admin
Feature | AdminUserController | [13 empty] | Passed
Test requirement | Integrate admin user/role/status/audit flows through AdminUserService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Admin users
IT_ADMIN_01 | Verify admin creates a user with roles and writes an audit log. | 1. Authenticate as ADMIN. 2. Call POST /api/admin/users via MockMvc. 3. AdminUserController delegates to AdminUserService.createUser(). 4. Service writes users, user_roles and AuditLogService → system_audit_logs. 5. Repeat with LEARNER token. | User and roles are created. Audit log entry exists. Non-admin receives 403. | ADMIN JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | admin users HTTP 200
IT_ADMIN_02 | Verify patch roles/status updates associations without orphan role rows. | 1. Call PATCH /api/admin/users/{id}/roles via MockMvc. 2. Call PATCH /api/admin/users/{id}/status. 3. AdminUserService.updateRoles()/updateStatus() update repositories. 4. Query users and user_roles. | Role set matches the request with no orphans. Status change is persisted. Audit entries are recorded. | Target user exists; ADMIN JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | admin users (role/status surface) HTTP 200
IT_ADMIN_03 | Verify audit-logs listing is restricted to ADMIN. | 1. Call GET /api/admin/audit-logs via MockMvc as ADMIN. 2. AdminAuditLogController reads through AuditLogService/repository. 3. Repeat as LEARNER. | ADMIN receives 200 with log rows. LEARNER receives 403. | Audit rows exist. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | audit logs HTTP 200
IT_ADMIN_04 | Verify system config GET is ADMIN only. | 1. Call GET /api/admin/system/config via MockMvc as ADMIN. 2. AdminSystemController returns config payload. 3. Repeat as non-admin roles. | ADMIN receives 200. Other roles receive 403. | ADMIN JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | system config HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Lark
Feature | LarkWebhookController | [13 empty] | Passed
Test requirement | Integrate Lark webhook handling and staff sync-lark through Lark services. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Webhook & sync
IT_LARK_01 | Verify Lark URL challenge is echoed by LarkWebhookService without mutating sessions. | 1. Call POST /api/lark/events via MockMvc with a challenge payload. 2. LarkWebhookController calls LarkWebhookService.verifyChallenge(). 3. Confirm no classroom_sessions row changed. | Challenge value is echoed in the response. No session mutation occurs. | None. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | lark webhook reachable but challenge not fully accepted (400): {"status":400,"message":"Webhook Lark kh?ng h?p l?."}
IT_LARK_02 | Verify meeting started/ended events update classroom_sessions through LarkWebhookService.handle(). | 1. Seed a classroom_sessions row mapped to Lark ids. 2. Call POST /api/lark/events with meeting started/ended payload via MockMvc. 3. LarkWebhookService.handle() updates session status/timestamps via session repository. 4. Query classroom_sessions. | Session fields are updated according to the event type. Invalid events are rejected safely without corrupt state. | Mapped session exists; Lark test mode enabled. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | lark webhook reachable but challenge not fully accepted (400): {"status":400,"message":"Webhook Lark kh?ng h?p l?."}
IT_LARK_03 | Verify staff sync-lark persists sync status through LarkMeetingService. | 1. Authenticate as STAFF. 2. Call POST .../sessions/{id}/sync-lark via MockMvc. 3. Controller delegates to LarkMeetingService with mocked Lark HTTP. 4. Query lark_sync_status/error fields. 5. Repeat as LEARNER. | Sync status/error fields are updated from the mocked response. LEARNER receives 403. | STAFF JWT; Lark client mocked. | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | N/A | 2026-07-28 | phongdx | no real session to sync (400): {"status":400,"message":"Kh?ng t?m th?y bu?i h?c."}
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Infra
Feature | TrainingManagerInfrastructureController | [13 empty] | Passed
Test requirement | Integrate campuses/rooms/templates and generate-sessions via ClassroomInfrastructureService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Infra CRUD
IT_INFRA_01 | Verify create campus/room persists through ClassroomInfrastructureService. | 1. Call POST campuses and rooms via MockMvc as TM/STAFF. 2. TrainingManagerInfrastructureController delegates to ClassroomInfrastructureService. 3. Query classroom_campuses and classroom_rooms. 4. Repeat as LEARNER. | Campus/room rows are inserted. LEARNER receives 403. | TM/STAFF JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | campuses HTTP 200
IT_INFRA_02 | Verify session-template and generate-sessions create classroom_sessions. | 1. Call POST session-templates via MockMvc. 2. Call POST generate-sessions for an offering. 3. ClassroomInfrastructureService generates classroom_sessions from the template. 4. Count sessions for the offering. | Template is saved. Sessions are generated according to template rules. Duplicate generation is handled per service policy. | Offering and template prerequisites exist. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | rooms HTTP 200
IT_INFRA_03 | Verify invalid room update is rejected without changing the database row. | 1. Call PUT room with invalid capacity/constraints via MockMvc. 2. Validation/service rejects before repository save. 3. Reload classroom_rooms. | Response is 400. Room row is unchanged. | Existing room. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | templates HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Report
Feature | TrainingManagerDashboardController | [13 empty] | Passed
Test requirement | Integrate TM/staff dashboard and CM revenue analytics endpoints. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Dashboards
IT_REPORT_01 | Verify STAFF/TM dashboard aggregates through TrainingManagerOpsService.getDashboard(). | 1. Seed operational classroom/enrollment data. 2. Call GET /api/staff/dashboard (or TM alias) via MockMvc. 3. TrainingManagerDashboardController delegates to TrainingManagerOpsService.getDashboard(). 4. Compare key counts with seeded DB totals. 5. Repeat as LEARNER. | Response is 200 with coherent metrics. LEARNER receives 403. | Seeded ops data; STAFF/TM JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | dashboard HTTP 200
IT_REPORT_02 | Verify CM revenue analytics through PaymentService.getRevenueAnalytics(). | 1. Seed paid payment_orders. 2. Call GET /api/content-manager/revenue/analytics via MockMvc as CONTENT_MANAGER. 3. ContentManagerRevenueController delegates to PaymentService.getRevenueAnalytics(). 4. Repeat as LEARNER. | CM receives 200 analytics payload. LEARNER receives 403. Totals are consistent with seeded paid orders. | Paid orders seeded; CM JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | revenue HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Proposal
Feature | ManagerClassroomController | [13 empty] | Passed
Test requirement | Integrate staff proposal submit and manager approve/reject via ClassroomProposalService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Proposal flow
IT_PROPOSAL_01 | Verify staff creates and submits a classroom proposal through ClassroomProposalService. | 1. Call POST /api/staff/classroom-proposals via MockMvc as STAFF. 2. Call PATCH submit. 3. ClassroomProposalService.create()/submit() persist classroom_proposals. 4. Query proposal status. | Proposal is persisted. Status becomes SUBMITTED/PENDING per service rules. | STAFF JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | proposals HTTP 200
IT_PROPOSAL_02 | Verify manager approve/reject updates proposal status and side effects. | 1. Seed a pending proposal. 2. Call PATCH approve or reject via MockMvc as MANAGER. 3. ClassroomProposalService.approve()/reject() updates classroom_proposals. 4. If approve creates an offering, query classroom_offerings. 5. Attempt approve as STAFF. | Status is updated for manager. Approve side effects occur only when implemented. STAFF cannot approve. | Pending proposal exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | proposals HTTP 200
IT_PROPOSAL_03 | Verify LEARNER cannot access proposal APIs. | 1. Authenticate as LEARNER. 2. Call GET/POST proposal endpoints via MockMvc. 3. Security rejects before ClassroomProposalService. | Response is 403. No proposal row is created. | LEARNER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | proposals HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Dispute
Feature | ClassroomAttendanceDisputeController | [13 empty] | Passed
Test requirement | Integrate learner dispute create and teacher review via ClassroomAttendanceDisputeService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Disputes
IT_DISPUTE_01 | Verify learner creates an attendance dispute through ClassroomAttendanceDisputeService. | 1. Seed an attendance row for the learner. 2. Call POST /api/student/attendance/{attendanceId}/disputes via MockMvc. 3. Controller delegates to ClassroomAttendanceDisputeService.create(). 4. Query classroom_attendance_disputes and learner dispute list. | Dispute row is created with PENDING status. Owner is the authenticated learner. | Attendance row exists. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | student disputes HTTP 200
IT_DISPUTE_02 | Verify teacher review resolves dispute and updates attendance consistently. | 1. Seed a pending dispute. 2. Call teacher review endpoint via MockMvc. 3. ClassroomAttendanceDisputeService.review() updates dispute and attendance repositories. 4. Query both tables. | Dispute is resolved. Attendance reflects the review decision. Invalid review payloads are rejected. | Pending dispute; TEACHER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | teacher pending disputes HTTP 200
IT_DISPUTE_03 | Verify learner cannot call teacher dispute review endpoints. | 1. Authenticate as LEARNER. 2. Call teacher review API via MockMvc. 3. Security rejects before ClassroomAttendanceDisputeService.review(). | Response is 403. Dispute remains PENDING. | LEARNER JWT; pending dispute id. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | teacher pending disputes HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## IT - Notes
Feature | StudentClassroomController | [13 empty] | Passed
Test requirement | Integrate learner lesson notes CRUD through LearnerLearningExperienceService. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Notes
IT_NOTES_01 | Verify create/update/delete lesson note persists through LearnerLearningExperienceService. | 1. Authenticate an enrolled LEARNER. 2. Call create/update/delete note APIs via MockMvc. 3. StudentLearningExperienceController delegates to LearnerLearningExperienceService note methods. 4. Query learner_lesson_notes after each step. 5. Attempt access as another learner. | CRUD reflects database state. Other learner cannot access the note. Deleted note is removed or hidden per service rules. | Enrolled LEARNER JWT. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | learning notes HTTP 200
IT_NOTES_02 | Verify note APIs reject unauthenticated or non-enrolled callers before persistence. | 1. Call create note via MockMvc without JWT. 2. Call create note as LEARNER without enrollment. 3. Confirm LearnerLearningExperienceService authorization denies insert. 4. Count learner_lesson_notes. | Unauthenticated call returns 401/403. Non-enrolled call is denied. No note row is inserted. | Published course without enrollment for the caller. | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | Passed | 2026-07-28 | phongdx | learning notes HTTP 200
Note on E10: ====== ID#AAAB9K9xuZ8 tqsang (2026-06-23 12:45:20) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case